## # Surveys per Outfall Area
Outfall Area | January | February | March | April | May | June | July | August | September | October | November | December | Grand Total
MS4-CAR-059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
MS4-CAR-069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
MS4-CAR-070 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 10
MS4-CAR-072 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 10
MS4-HST01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
MS4-SDG-072 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 10
MS4-SDG-074 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 9
MS4-SDG-077 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 9
MS4-SDG-080 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 9
MS4-SDG-084 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 10
MS4-SDG-085 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 9
MS4-SDG-275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
MS4-SDR-036 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
MS4-SDR-064 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
MS4-SDR-097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
MS4-SDR-098 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 10
MS4-SDR-127 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 11
MS4-SDR-203A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
MS4-SDR-204A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
MS4-SDR-207 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 9
MS4-SDR-228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 3
MS4-SDR-568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 3
MS4-SLR-045 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 8
MS4-SLR-095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
MS4-SLR-152 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 4
MS4-SLR-154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 4
MS4-SLR-155 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 4
MS4-SLR-159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 3
MS4-SWT-019 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 9
MS4-SWT-023 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
MS4-SWT-030 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 9
MS4-SWT-055 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 8
MS4-SWT-235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Total | 0 | 7 | 17 | 15 | 12 | 15 | 15 | 21 | 21 | 21 | 11 | 18 | 173

## Survey Periods
Outfall | City | Record ID | Day of Week | Revised Outfall | Month (Initial Survey) | Initial Survey Period Start Date/Time | Initial Survey Period End Date/Time | # of Follow-up Issues Observed | Follow-up Survey Period Start Date/Time | Follow-up Survey Period End Date/Time | # of Issues Corrected at time of Follow-up | # of Follow-up Requiring >1 Follow-up
SDG-084 | 4S Ranch | DPW2015-WPSWIN-00607 | Tuesday | MS4-SDG-084 | February | 2019-02-19 | 2019-02-19 02:00 | TBD | 2019-03-19 | 2019-03-19 02:00 | TBD | TBD
SWT-023 | Bonita | DPW2015-WPSWIN-00625 | Tuesday | MS4-SWT-023 | February | 2019-02-19 05:00 | 2019-02-19 07:00 | TBD | 2019-03-19 05:00 | 2019-03-19 07:00 | TBD | TBD
SDR-036 | Lakeside | DPW2015-WPSWIN-00717 | Tuesday | MS4-SDR-036 | February | 2019-02-19 07:00 | 2019-02-19 09:00 | TBD | 2019-03-19 07:00 | 2019-03-19 09:00 | TBD | TBD
SDR-207 | Lakeside | DPW2015-WPSWIN-00738 | Tuesday | MS4-SDR-207 | February | 2019-02-19 08:00 | 2019-02-19 10:00 | TBD | 2019-03-19 08:00 | 2019-03-19 10:00 | TBD | TBD
SWT-055 | Spring Valley | DPW2015-WPSWIN-00631 | Wednesday | MS4-SWT-055 | February | 2019-02-20 02:00 | 2019-02-20 04:00 | TBD | 2019-03-20 02:00 | 2019-03-20 04:00 | TBD | TBD
SDR-064 | Lakeside | DPW2015-WPSWIN-00677 | Thursday | MS4-SDR-064 | February | 2019-02-28 05:00 | 2019-02-28 07:00 | TBD | 2019-03-28 05:00 | 2019-03-28 07:00 | TBD | TBD
SDR-127 | Lakeside | DPW2015-WPSWIN-00733 | Thursday | MS4-SDR-127 | February | 2019-02-28 07:00 | 2019-02-28 09:00 | TBD | 2019-03-28 07:00 | 2019-03-28 09:00 | TBD | TBD
SLR-155 | Pala Mesa | DPW2015-WPSWIN-00758 | Saturday | MS4-SLR-155 | March | 2019-03-16 03:00 | 2019-03-16 05:00 | TBD | 2019-04-13 03:00 | 2019-04-13 05:00 | TBD | TBD
SDG-074 | 4S Ranch | DPW2015-WPSWIN-00604 | Saturday | MS4-SDG-074 | March | 2019-03-16 05:00 | 2019-03-16 07:00 | TBD | 2019-04-13 05:00 | 2019-04-13 07:00 | TBD | TBD
CAR-070 | San Marcos | DPW2015-WPSWIN-00721 | Saturday | MS4-CAR-070 | March | 2019-03-16 09:00 | 2019-03-16 11:00 | TBD | 2019-04-13 09:00 | 2019-04-13 11:00 | TBD | TBD
CAR-072 | San Marcos | DPW2015-WPSWIN-00724 | Saturday | MS4-CAR-072 | March | 2019-03-16 20:00 | 2019-03-16 22:00 | TBD | 2019-04-13 20:00 | 2019-04-13 22:00 | TBD | TBD
SDG-085 | 4S Ranch | DPW2015-WPSWIN-00608 | Saturday | MS4-SDG-085 | March | 2019-03-16 21:00 | 2019-03-16 23:00 | TBD | 2019-04-13 21:00 | 2019-04-13 23:00 | TBD | TBD
SDG-072 | Bonita | DPW2015-WPSWIN-00603 | Saturday | MS4-SDG-072 | March | 2019-03-16 23:00 | 2019-03-17 01:00 | TBD | 2019-04-13 23:00 | 2019-04-14 01:00 | TBD | TBD
SDR-207 | Lakeside | DPW2015-WPSWIN-00738 | Tuesday | MS4-SDR-207 | March | 2019-03-19 08:00 | 2019-03-19 10:00 | TBD | 2019-04-16 08:00 | 2019-04-16 10:00 | TBD | TBD
SWT-055 | Spring Valley | DPW2015-WPSWIN-00631 | Wednesday | MS4-SWT-055 | March | 2019-03-27 02:00 | 2019-03-27 04:00 | TBD | 2019-04-24 02:00 | 2019-04-24 04:00 | TBD | TBD
SDG-084 | 4S Ranch | DPW2015-WPSWIN-00607 | Thursday | MS4-SDG-084 | March | 2019-03-28 | 2019-03-28 02:00 | TBD | 2019-04-25 | 2019-04-25 02:00 | TBD | TBD
SLR-152 | Pala Mesa | DPW2015-WPSWIN-00756 | Thursday | MS4-SLR-152 | March | 2019-03-28 02:00 | 2019-03-28 04:00 | TBD | 2019-04-25 02:00 | 2019-04-25 04:00 | TBD | TBD
SDG-077 | 4S Ranch | DPW2015-WPSWIN-00606 | Thursday | MS4-SDG-077 | March | 2019-03-28 05:00 | 2019-03-28 07:00 | TBD | 2019-04-25 05:00 | 2019-04-25 07:00 | TBD | TBD
SDR-127 | Lakeside | DPW2015-WPSWIN-00733 | Thursday | MS4-SDR-127 | March | 2019-03-28 07:00 | 2019-03-28 09:00 | TBD | 2019-04-25 07:00 | 2019-04-25 09:00 | TBD | TBD
SDR-098 | 4S Ranch | DPW2015-WPSWIN-00731 | Friday | MS4-SDR-098 | March | 2019-03-29 02:00 | 2019-03-29 04:00 | TBD | 2019-04-26 02:00 | 2019-04-26 04:00 | TBD | TBD
SWT-030 | Spring Valley | DPW2015-WPSWIN-00637 | Friday | MS4-SWT-030 | March | 2019-03-29 04:00 | 2019-03-29 06:00 | TBD | 2019-04-26 04:00 | 2019-04-26 06:00 | TBD | TBD
SLR-045 | Escondido | DPW2017-WPSWIN-01357 | Friday | MS4-SLR-045 | March | 2019-03-29 06:00 | 2019-03-29 08:00 | TBD | 2019-04-26 06:00 | 2019-04-26 08:00 | TBD | TBD
SWT-019 | Bonita | DPW2015-WPSWIN-00622 | Friday | MS4-SWT-019 | March | 2019-03-29 19:00 | 2019-03-29 21:00 | TBD | 2019-04-26 19:00 | 2019-04-26 21:00 | TBD | TBD
SDG-080 | 4S Ranch | DPW2015-WPSWIN-00660 | Friday | MS4-SDG-080 | March | 2019-03-29 22:00 | 2019-03-31 | TBD | 2019-04-26 22:00 | 2019-04-28 | TBD | TBD
SDG-072 | 4S Ranch | DPW2015-WPSWIN-00603 | Wednesday | MS4-SDG-072 | April | 2019-04-10 | 2019-04-10 02:00 | TBD | 2019-05-08 | 2019-05-08 02:00 | TBD | TBD
SDR-098 | Lakeside | DPW2015-WPSWIN-00731 | Wednesday | MS4-SDR-098 | April | 2019-04-10 02:00 | 2019-04-10 04:00 | TBD | 2019-05-08 02:00 | 2019-05-08 04:00 | TBD | TBD
SDG-077 | 4S Ranch | DPW2015-WPSWIN-00606 | Thursday | MS4-SDG-077 | April | 2019-04-11 05:00 | 2019-04-11 07:00 | TBD | 2019-05-09 05:00 | 2019-05-09 07:00 | TBD | TBD
SDG-074 | 4S Ranch | DPW2015-WPSWIN-00604 | Thursday | MS4-SDG-074 | April | 2019-04-11 05:00 | 2019-04-11 07:00 | TBD | 2019-05-09 05:00 | 2019-05-09 07:00 | TBD | TBD
SDG-080 | 4S Ranch | DPW2015-WPSWIN-00660 | Thursday | MS4-SDG-080 | April | 2019-04-11 06:00 | 2019-04-11 08:00 | TBD | 2019-05-09 06:00 | 2019-05-09 08:00 | TBD | TBD
CAR-072 | San Marcos | DPW2015-WPSWIN-00724 | Thursday PM | MS4-CAR-072 | April | 2019-04-11 20:00 | 2019-04-11 22:00 | TBD | 2019-05-09 20:00 | 2019-05-09 22:00 | TBD | TBD
CAR-070 | San Marcos | DPW2015-WPSWIN-00721 | Thursday PM | MS4-CAR-070 | April | 2019-04-11 23:00 | 2019-04-13 01:00 | TBD | 2019-05-09 23:00 | 2019-05-11 01:00 | TBD | TBD
SDG-084 | 4S Ranch | DPW2015-WPSWIN-00607 | Monday | MS4-SDG-084 | April | 2019-04-15 | 2019-04-15 02:00 | TBD | 2019-05-13 | 2019-05-13 02:00 | TBD | TBD
SDG-085 | 4S Ranch | DPW2015-WPSWIN-00608 | Monday | MS4-SDG-085 | April | 2019-04-15 01:00 | 2019-04-15 03:00 | TBD | 2019-05-13 01:00 | 2019-05-13 03:00 | TBD | TBD
SLR-045 | Escondido | DPW2017-WPSWIN-01357 | Monday | MS4-SLR-045 | April | 2019-04-15 04:00 | 2019-04-15 06:00 | TBD | 2019-05-13 04:00 | 2019-05-13 06:00 | TBD | TBD
SWT-055 | Spring Valley | DPW2015-WPSWIN-00631 | Monday | MS4-SWT-055 | April | 2019-04-15 01:00 | 2019-04-15 03:00 | TBD | 2019-05-13 01:00 | 2019-05-13 03:00 | TBD | TBD
SWT-030 | Spring Valley | DPW2015-WPSWIN-00637 | Monday | MS4-SWT-030 | April | 2019-04-15 04:00 | 2019-04-15 06:00 | TBD | 2019-05-13 04:00 | 2019-05-13 06:00 | TBD | TBD
SDR-127 | Lakeside | DPW2015-WPSWIN-00733 | Tuesday | MS4-SDR-127 | April | 2019-04-16 07:00 | 2019-04-16 09:00 | TBD | 2019-05-14 07:00 | 2019-05-14 09:00 | TBD | TBD
SDR-207 | Lakeside | DPW2015-WPSWIN-00738 | Tuesday | MS4-SDR-207 | April | 2019-04-16 09:00 | 2019-04-16 12:00 | TBD | 2019-05-14 09:00 | 2019-05-14 12:00 | TBD | TBD
SWT-019 | Bonita | DPW2015-WPSWIN-00622 | Saturday | MS4-SWT-019 | April | 2019-04-20 16:00 | 2019-04-20 18:00 | TBD | 2019-05-18 16:00 | 2019-05-18 18:00 | TBD | TBD
CAR-072 | San Marcos | DPW2015-WPSWIN-00724 | Wednesday | MS4-CAR-072 | May | 2019-05-15 | 2019-05-15 02:00 | TBD | 2019-06-12 | 2019-06-12 02:00 | TBD | TBD
SWT-019 | Spring Valley | DPW2015-WPSWIN-00622 | Wednesday | MS4-SWT-019 | May | 2019-05-15 03:00 | 2019-05-15 05:00 | TBD | 2019-06-12 03:00 | 2019-06-12 05:00 | TBD | TBD
SWT-030 | Spring Valley | DPW2015-WPSWIN-00637 | Wednesday | MS4-SWT-030 | May | 2019-05-15 05:00 | 2019-05-15 07:00 | TBD | 2019-06-12 05:00 | 2019-06-12 07:00 | TBD | TBD
SDG-077 | 4S Ranch | DPW2015-WPSWIN-00606 | Thursday | MS4-SDG-077 | May | 2019-05-23 05:00 | 2019-05-23 07:00 | TBD | 2019-06-20 05:00 | 2019-06-20 07:00 | TBD | TBD
SDG-074 | 4S Ranch | DPW2015-WPSWIN-00604 | Thursday | MS4-SDG-074 | May | 2019-05-23 05:00 | 2019-05-23 07:00 | TBD | 2019-06-20 05:00 | 2019-06-20 07:00 | TBD | TBD
SDG-080 | 4S Ranch | DPW2015-WPSWIN-00660 | Thursday | MS4-SDG-080 | May | 2019-05-23 06:00 | 2019-05-23 08:00 | TBD | 2019-06-20 06:00 | 2019-06-20 08:00 | TBD | TBD
SDG-084 | 4S Ranch | DPW2015-WPSWIN-00607 | Thursday | MS4-SDG-084 | May | 2019-05-23 22:00 | 2019-05-25 | TBD | 2019-06-20 22:00 | 2019-06-22 | TBD | TBD
SDG-072 | 4S Ranch | DPW2015-WPSWIN-00603 | Friday | MS4-SDG-072 | May | 2019-05-24 | 2019-05-24 01:30 | TBD | 2019-06-21 | 2019-06-21 01:30 | TBD | TBD
SDG-085 | 4S Ranch | DPW2015-WPSWIN-00608 | Friday | MS4-SDG-085 | May | 2019-05-24 01:30 | 2019-05-24 03:00 | TBD | 2019-06-21 01:30 | 2019-06-21 03:00 | TBD | TBD
CAR-070 | San Marcos | DPW2015-WPSWIN-00721 | Saturday | MS4-CAR-070 | May | 2019-05-25 09:00 | 2019-05-25 11:00 | TBD | 2019-06-22 09:00 | 2019-06-22 11:00 | TBD | TBD
SDR-098 | Lakeside | DPW2015-WPSWIN-00731 | Sunday | MS4-SDR-098 | May | 2019-05-26 | 2019-05-26 02:00 | TBD | 2019-06-23 | 2019-06-23 02:00 | TBD | TBD
SDR-127 | Lakeside | DPW2015-WPSWIN-00733 | Sunday | MS4-SDR-127 | May | 2019-05-26 02:00 | 2019-05-26 04:00 | TBD | 2019-06-23 02:00 | 2019-06-23 04:00 | TBD | TBD
SDR-127 | Lakeside | DPW2015-WPSWIN-00733 | Monday | MS4-SDR-127 | June | 2019-06-10 21:00 | 2019-06-10 23:00 | TBD | 2019-07-08 21:00 | 2019-07-08 23:00 | TBD | TBD
SWT-030 | Spring Valley | DPW2015-WPSWIN-00637 | Tuesday | MS4-SWT-030 | June | 2019-06-11 | 2019-06-11 02:00 | TBD | 2019-07-09 | 2019-07-09 02:00 | TBD | TBD
SWT-055 | Spring Valley | DPW2015-WPSWIN-00631 | Tuesday | MS4-SWT-055 | June | 2019-06-11 | 2019-06-11 02:00 | TBD | 2019-07-09 | 2019-07-09 02:00 | TBD | TBD
CAR-072 | San Marcos | DPW2015-WPSWIN-00724 | Tuesday | MS4-CAR-072 | June | 2019-06-11 | 2019-06-11 02:00 | TBD | 2019-07-09 | 2019-07-09 02:00 | TBD | TBD
SDR-098 | Lakeside | DPW2015-WPSWIN-00731 | Wednesday | MS4-SDR-098 | June | 2019-06-12 | 2019-06-12 02:00 | TBD | 2019-07-10 | 2019-07-10 02:00 | TBD | TBD
SDR-207 | Lakeside | DPW2015-WPSWIN-00738 | Wednesday | MS4-SDR-207 | June | 2019-06-12 03:00 | 2019-06-12 05:00 | TBD | 2019-07-10 03:00 | 2019-07-10 05:00 | TBD | TBD
SDG-085 | 4S Ranch | DPW2015-WPSWIN-00608 | Thursday | MS4-SDG-085 | June | 2019-06-13 02:00 | 2019-06-13 04:00 | TBD | 2019-07-11 02:00 | 2019-07-11 04:00 | TBD | TBD
SDG-072 | 4S Ranch | DPW2015-WPSWIN-00603 | Thursday | MS4-SDG-072 | June | 2019-06-13 07:00 | 2019-06-13 09:00 | TBD | 2019-07-11 07:00 | 2019-07-11 09:00 | TBD | TBD
SDG-074 | 4S Ranch | DPW2015-WPSWIN-00604 | Thursday | MS4-SDG-074 | June | 2019-06-13 09:00 | 2019-06-13 11:00 | TBD | 2019-07-11 09:00 | 2019-07-11 11:00 | TBD | TBD
SDG-080 | San Diego | DPW2015-WPSWIN-00660 | Thursday | MS4-SDG-080 | June | 2019-06-13 04:00 | 2019-06-13 06:00 | TBD | 2019-07-11 04:00 | 2019-07-11 06:00 | TBD | TBD
CAR-070 | San Marcos | DPW2015-WPSWIN-00721 | Thursday | MS4-CAR-070 | June | 2019-06-13 22:00 | 2019-06-15 | TBD | 2019-07-11 22:00 | 2019-07-13 | TBD | TBD
SLR-045 | Escondido | DPW2017-WPSWIN-01357 | Friday | MS4-SLR-045 | June | 2019-06-14 | 2019-06-14 02:00 | TBD | 2019-07-12 | 2019-07-12 02:00 | TBD | TBD
SDG-077 | 4S Ranch | DPW2015-WPSWIN-00606 | Friday | MS4-SDG-077 | June | 2019-06-14 05:00 | 2019-06-14 07:00 | TBD | 2019-07-12 05:00 | 2019-07-12 07:00 | TBD | TBD
SDG-084 | 4S Ranch | DPW2015-WPSWIN-00607 | Saturday | MS4-SDG-084 | June | 2019-06-15 21:00 | 2019-06-15 23:00 | TBD | 2019-07-13 21:00 | 2019-07-13 23:00 | TBD | TBD
SWT-019 | Spring Valley | DPW2015-WPSWIN-00622 | Sunday | MS4-SWT-019 | June | 2019-06-16 06:00 | 2019-06-16 08:00 | TBD | 2019-07-14 06:00 | 2019-07-14 08:00 | TBD | TBD
SDR-207 | Lakeside | DPW2015-WPSWIN-00738 | Monday | MS4-SDR-207 | July | 2019-07-08 05:00 | 2019-07-08 07:00 | TBD | 2019-08-05 05:00 | 2019-08-05 07:00 | TBD | TBD
SDG-074 | 4S Ranch | DPW2015-WPSWIN-00604 | Monday | MS4-SDG-074 | July | 2019-07-08 05:00 | 2019-07-08 07:00 | TBD | 2019-08-05 05:00 | 2019-08-05 07:00 | TBD | TBD
SDG-072 | 4S Ranch | DPW2015-WPSWIN-00603 | Monday | MS4-SDG-072 | July | 2019-07-08 07:00 | 2019-07-08 09:00 | TBD | 2019-08-05 07:00 | 2019-08-05 09:00 | TBD | TBD
CAR-070 | San Marcos | DPW2015-WPSWIN-00721 | Tuesday | MS4-CAR-070 | July | 2019-07-09 | 2019-07-09 02:00 | TBD | 2019-08-06 | 2019-08-06 02:00 | TBD | TBD
SDG-077 | 4S Ranch | DPW2015-WPSWIN-00606 | Tuesday | MS4-SDG-077 | July | 2019-07-09 05:00 | 2019-07-09 07:00 | TBD | 2019-08-06 05:00 | 2019-08-06 07:00 | TBD | TBD
SWT-055 | Spring Valley | DPW2015-WPSWIN-00631 | Tuesday | MS4-SWT-055 | July | 2019-07-09 | 2019-07-09 02:00 | TBD | 2019-08-06 | 2019-08-06 02:00 | TBD | TBD
SDR-098 | Lakeside | DPW2015-WPSWIN-00731 | Tuesday | MS4-SDR-098 | July | 2019-07-09 03:00 | 2019-07-09 05:00 | TBD | 2019-08-06 03:00 | 2019-08-06 05:00 | TBD | TBD
SLR-045 | Escondido | DPW2017-WPSWIN-01357 | Wednesday | MS4-SLR-045 | July | 2019-07-10 03:00 | 2019-07-10 05:00 | TBD | 2019-08-07 03:00 | 2019-08-07 05:00 | TBD | TBD
SDR-127 | Lakeside | DPW2015-WPSWIN-00733 | Wednesday | MS4-SDR-127 | July | 2019-07-10 01:30 | 2019-07-10 03:30 | TBD | 2019-08-07 01:30 | 2019-08-07 03:30 | TBD | TBD
SDG-085 | 4S Ranch | DPW2015-WPSWIN-00608 | Friday | MS4-SDG-085 | July | 2019-07-12 03:00 | 2019-07-12 05:00 | TBD | 2019-08-09 03:00 | 2019-08-09 05:00 | TBD | TBD
SWT-030 | Spring Valley | DPW2015-WPSWIN-00637 | Saturday | MS4-SWT-030 | July | 2019-07-13 15:00 | 2019-07-13 17:00 | TBD | 2019-08-10 15:00 | 2019-08-10 17:00 | TBD | TBD
SDG-084 | 4S Ranch | DPW2015-WPSWIN-00607 | Saturday | MS4-SDG-084 | July | 2019-07-13 21:00 | 2019-07-13 23:00 | TBD | 2019-08-10 21:00 | 2019-08-10 23:00 | TBD | TBD
CAR-072 | San Marcos | DPW2015-WPSWIN-00724 | Saturday | MS4-CAR-072 | July | 2019-07-13 | 2019-07-13 02:00 | TBD | 2019-08-10 | 2019-08-10 02:00 | TBD | TBD
SDG-080 | 4S Ranch | DPW2015-WPSWIN-00660 | Saturday | MS4-SDG-080 | July | 2019-07-13 05:00 | 2019-07-13 07:00 | TBD | 2019-08-10 05:00 | 2019-08-10 07:00 | TBD | TBD
SWT-019 | Spring Valley | DPW2015-WPSWIN-00622 | Monday | MS4-SWT-019 | July | 2019-07-15 07:00 | 2019-07-15 09:00 | TBD | 2019-08-12 07:00 | 2019-08-12 09:00 | TBD | TBD
SDG-072 | 4S Ranch | DPW2015-WPSWIN-00603 | Saturday | MS4-SDG-072 | August | 2019-08-17 11:00 | 2019-08-17 13:00 | TBD | 2019-09-14 11:00 | 2019-09-14 13:00 | TBD | TBD
SDG-077 | 4S Ranch | DPW2015-WPSWIN-00606 | Saturday | MS4-SDG-077 | August | 2019-08-17 17:00 | 2019-08-17 19:00 | TBD | 2019-09-14 17:00 | 2019-09-14 19:00 | TBD | TBD
SDR-568 | Lakeside | DPW2019-WPSWIN-02804 | Monday | MS4-SDR-568 | August | 2019-08-19 01:00 | 2019-08-19 03:00 | TBD | 2019-09-16 01:00 | 2019-09-16 03:00 | TBD | TBD
SDR-228 | Lakeside | DPW2015-WPSWIN-00709 | Monday | MS4-SDR-228 | August | 2019-08-19 03:00 | 2019-08-19 05:00 | TBD | 2019-09-16 03:00 | 2019-09-16 05:00 | TBD | TBD
SLR-155 | Escondido | DPW2015-WPSWIN-00758 | Monday | MS4-SLR-155 | August | 2019-08-19 06:00 | 2019-08-19 08:00 | TBD | 2019-09-16 06:00 | 2019-09-16 08:00 | TBD | TBD
SLR-159 | Escondido | DPW2019-WPSWIN-02805 | Monday | MS4-SLR-159 | August | 2019-08-19 08:00 | 2019-08-19 10:00 | TBD | 2019-09-16 08:00 | 2019-09-16 10:00 | TBD | TBD
SDG-080 | 4S Ranch | DPW2015-WPSWIN-00660 | Monday-Tuesday | MS4-SDG-080 | August | 2019-08-19 22:00 | 2019-08-21 | TBD | 2019-09-16 22:00 | 2019-09-18 | TBD | TBD
SDG-084 | 4S Ranch | DPW2015-WPSWIN-00607 | Tuesday | MS4-SDG-084 | August | 2019-08-20 | 2019-08-20 02:00 | TBD | 2019-09-17 | 2019-09-17 02:00 | TBD | TBD
SWT-030 | Spring Valley | DPW2015-WPSWIN-00637 | Tuesday | MS4-SWT-030 | August | 2019-08-20 03:00 | 2019-08-20 05:00 | TBD | 2019-09-17 03:00 | 2019-09-17 05:00 | TBD | TBD
SWT-055 | Spring Valley | DPW2015-WPSWIN-00631 | Tuesday | MS4-SWT-055 | August | 2019-08-20 05:00 | 2019-08-20 07:00 | TBD | 2019-09-17 05:00 | 2019-09-17 07:00 | TBD | TBD
CAR-070 | San Marcos | DPW2015-WPSWIN-00721 | Tuesday | MS4-CAR-070 | August | 2019-08-20 21:00 | 2019-08-20 23:00 | TBD | 2019-09-17 21:00 | 2019-09-17 23:00 | TBD | TBD
CAR-072 | San Marcos | DPW2015-WPSWIN-00724 | Tuesday-Wednesday | MS4-CAR-072 | August | 2019-08-20 23:00 | 2019-08-22 01:00 | TBD | 2019-09-17 23:00 | 2019-09-19 01:00 | TBD | TBD
SDR-098 | Lakeside | DPW2015-WPSWIN-00731 | Wednesday | MS4-SDR-098 | August | 2019-08-21 04:00 | 2019-08-21 06:00 | TBD | 2019-09-18 04:00 | 2019-09-18 06:00 | TBD | TBD
SDR-207 | Lakeside | DPW2015-WPSWIN-00738 | Wednesday | MS4-SDR-207 | August | 2019-08-21 05:00 | 2019-08-21 07:00 | TBD | 2019-09-18 05:00 | 2019-09-18 07:00 | TBD | TBD
SWT-019 | Spring Valley | DPW2015-WPSWIN-00622 | Wednesday | MS4-SWT-019 | August | 2019-08-21 09:00 | 2019-08-21 11:00 | TBD | 2019-09-18 09:00 | 2019-09-18 11:00 | TBD | TBD
SDG-074 | 4S Ranch | DPW2015-WPSWIN-00604 | Friday | MS4-SDG-074 | August | 2019-08-23 03:00 | 2019-08-23 05:00 | TBD | 2019-09-20 03:00 | 2019-09-20 05:00 | TBD | TBD
SDG-085 | 4S Ranch | DPW2015-WPSWIN-00608 | Friday | MS4-SDG-085 | August | 2019-08-23 05:00 | 2019-08-23 07:00 | TBD | 2019-09-20 05:00 | 2019-09-20 07:00 | TBD | TBD
SLR-154 | Escondido | DPW2015-WPSWIN-00757 | Friday | MS4-SLR-154 | August | 2019-08-23 04:00 | 2019-08-23 06:00 | TBD | 2019-09-20 04:00 | 2019-09-20 06:00 | TBD | TBD
SLR-152 | Escondido | DPW2015-WPSWIN-00756 | Friday | MS4-SLR-152 | August | 2019-08-23 06:00 | 2019-08-23 08:00 | TBD | 2019-09-20 06:00 | 2019-09-20 08:00 | TBD | TBD
SLR-045 | Escondido | DPW2017-WPSWIN-01357 | Friday | MS4-SLR-045 | August | 2019-08-23 08:00 | 2019-08-23 10:00 | TBD | 2019-09-20 08:00 | 2019-09-20 10:00 | TBD | TBD
SDR-127 | Lakeside | DPW2015-WPSWIN-00733 | Friday | MS4-SDR-127 | August | 2019-08-23 13:00 | 2019-08-23 15:00 | TBD | 2019-09-20 13:00 | 2019-09-20 15:00 | TBD | TBD
SDG-072 | 4S Ranch | DPW2015-WPSWIN-00603 | Wednesday | MS4-SDG-072 | September | 2019-09-11 11:00 | 2019-09-11 13:00 | TBD | 2019-10-09 11:00 | 2019-10-09 13:00 | TBD | TBD
SDG-074 | 4S Ranch | DPW2015-WPSWIN-00604 | Friday | MS4-SDG-074 | September | 2019-09-13 03:00 | 2019-09-13 05:00 | TBD | 2019-10-11 03:00 | 2019-10-11 05:00 | TBD | TBD
SDR-098 | Lakeside | DPW2015-WPSWIN-00731 | Friday | MS4-SDR-098 | September | 2019-09-13 13:00 | 2019-09-13 15:00 | TBD | 2019-10-11 13:00 | 2019-10-11 15:00 | TBD | TBD
SDR-568 | Lakeside | DPW2019-WPSWIN-02804 | Sunday | MS4-SDR-568 | September | 2019-09-15 04:00 | 2019-09-15 06:00 | TBD | 2019-10-13 04:00 | 2019-10-13 06:00 | TBD | TBD
SDR-207 | Lakeside | DPW2015-WPSWIN-00738 | Sunday | MS4-SDR-207 | September | 2019-09-15 06:00 | 2019-09-15 08:00 | TBD | 2019-10-13 06:00 | 2019-10-13 08:00 | TBD | TBD
SDR-228 | Lakeside | DPW2015-WPSWIN-00709 | Sunday | MS4-SDR-228 | September | 2019-09-15 08:00 | 2019-09-15 10:00 | TBD | 2019-10-13 08:00 | 2019-10-13 10:00 | TBD | TBD
SDR-127 | Lakeside | DPW2015-WPSWIN-00733 | Monday | MS4-SDR-127 | September | 2019-09-16 | 2019-09-16 02:00 | TBD | 2019-10-14 | 2019-10-14 02:00 | TBD | TBD
SDG-084 | 4S Ranch | DPW2015-WPSWIN-00607 | Monday | MS4-SDG-084 | September | 2019-09-16 | 2019-09-16 02:00 | TBD | 2019-10-14 | 2019-10-14 02:00 | TBD | TBD
SDG-085 | 4S Ranch | DPW2015-WPSWIN-00608 | Monday | MS4-SDG-085 | September | 2019-09-16 01:00 | 2019-09-16 03:00 | TBD | 2019-10-14 01:00 | 2019-10-14 03:00 | TBD | TBD
SDG-077 | 4S Ranch | DPW2015-WPSWIN-00606 | Monday | MS4-SDG-077 | September | 2019-09-16 20:00 | 2019-09-16 22:00 | TBD | 2019-10-14 20:00 | 2019-10-14 22:00 | TBD | TBD
SDG-080 | 4S Ranch | DPW2015-WPSWIN-00660 | Monday | MS4-SDG-080 | September | 2019-09-16 21:00 | 2019-09-16 23:00 | TBD | 2019-10-14 21:00 | 2019-10-14 23:00 | TBD | TBD
CAR-070 | San Marcos | DPW2015-WPSWIN-00721 | Tuesday | MS4-CAR-070 | September | 2019-09-17 02:00 | 2019-09-17 04:00 | TBD | 2019-10-15 02:00 | 2019-10-15 04:00 | TBD | TBD
SLR-155 | Escondido | DPW2015-WPSWIN-00758 | Tuesday | MS4-SLR-155 | September | 2019-09-17 01:00 | 2019-09-17 03:00 | TBD | 2019-10-15 01:00 | 2019-10-15 03:00 | TBD | TBD
SLR-045 | Escondido | DPW2017-WPSWIN-01357 | Tuesday | MS4-SLR-045 | September | 2019-09-17 02:00 | 2019-09-17 04:00 | TBD | 2019-10-15 02:00 | 2019-10-15 04:00 | TBD | TBD
CAR-072 | San Marcos | DPW2015-WPSWIN-00724 | Wednesday | MS4-CAR-072 | September | 2019-09-18 | 2019-09-18 02:00 | TBD | 2019-10-16 | 2019-10-16 02:00 | TBD | TBD
SWT-055 | Spring Valley | DPW2015-WPSWIN-00631 | Friday | MS4-SWT-055 | September | 2019-09-20 01:00 | 2019-09-20 03:00 | TBD | 2019-10-18 01:00 | 2019-10-18 03:00 | TBD | TBD
SWT-030 | Spring Valley | DPW2015-WPSWIN-00637 | Friday | MS4-SWT-030 | September | 2019-09-20 02:00 | 2019-09-20 04:00 | TBD | 2019-10-18 02:00 | 2019-10-18 04:00 | TBD | TBD
SWT-019 | Spring Valley | DPW2015-WPSWIN-00622 | Friday | MS4-SWT-019 | September | 2019-09-20 07:00 | 2019-09-20 09:00 | TBD | 2019-10-18 07:00 | 2019-10-18 09:00 | TBD | TBD
SLR-154 | Escondido | DPW2015-WPSWIN-00757 | Friday | MS4-SLR-154 | September | 2019-09-20 04:00 | 2019-09-20 06:00 | TBD | 2019-10-18 04:00 | 2019-10-18 06:00 | TBD | TBD
SLR-159 | Escondido | DPW2019-WPSWIN-02805 | Friday | MS4-SLR-159 | September | 2019-09-20 04:00 | 2019-09-20 06:00 | TBD | 2019-10-18 04:00 | 2019-10-18 06:00 | TBD | TBD
SLR-152 | Escondido | DPW2015-WPSWIN-00756 | Friday | MS4-SLR-152 | September | 2019-09-20 06:00 | 2019-09-20 08:00 | TBD | 2019-10-18 06:00 | 2019-10-18 08:00 | TBD | TBD
SLR-152 | Escondido | DPW2015-WPSWIN-00756 | Thursday | MS4-SLR-152 | October | 2019-10-03 03:00 | 2019-10-03 05:00 | TBD | 2019-10-31 03:00 | 2019-10-31 05:00 | TBD | TBD
SLR-155 | Escondido | DPW2015-WPSWIN-00758 | Thursday | MS4-SLR-155 | October | 2019-10-03 05:00 | 2019-10-03 07:00 | TBD | 2019-10-31 05:00 | 2019-10-31 07:00 | TBD | TBD
CAR-072 | San Marcos | DPW2015-WPSWIN-00724 | Friday | MS4-CAR-072 | October | 2019-10-04 03:00 | 2019-10-04 05:00 | TBD | 2019-11-01 03:00 | 2019-11-01 05:00 | TBD | TBD
CAR-070 | San Marcos | DPW2015-WPSWIN-00721 | Friday | MS4-CAR-070 | October | 2019-10-04 04:00 | 2019-10-04 06:00 | TBD | 2019-11-01 04:00 | 2019-11-01 06:00 | TBD | TBD
SDG-072 | 4S Ranch | DPW2015-WPSWIN-00603 | Friday | MS4-SDG-072 | October | 2019-10-04 21:00 | 2019-10-04 23:00 | TBD | 2019-11-01 21:00 | 2019-11-01 23:00 | TBD | TBD
SDG-080 | 4S Ranch | DPW2015-WPSWIN-00660 | Friday | MS4-SDG-080 | October | 2019-10-04 23:00 | 2019-10-06 01:00 | TBD | 2019-11-01 23:00 | 2019-11-03 01:00 | TBD | TBD
SDR-568 | Lakeside | DPW2019-WPSWIN-02804 | Sunday | MS4-SDR-568 | October | 2019-10-06 03:00 | 2019-10-06 05:00 | TBD | 2019-11-03 03:00 | 2019-11-03 05:00 | TBD | TBD
SDR-207 | Lakeside | DPW2015-WPSWIN-00738 | Sunday | MS4-SDR-207 | October | 2019-10-06 05:00 | 2019-10-06 07:00 | TBD | 2019-11-03 05:00 | 2019-11-03 07:00 | TBD | TBD
SDR-228 | Lakeside | DPW2015-WPSWIN-00709 | Sunday | MS4-SDR-228 | October | 2019-10-06 06:00 | 2019-10-06 08:00 | TBD | 2019-11-03 06:00 | 2019-11-03 08:00 | TBD | TBD
SWT-055 | Spring Valley | DPW2015-WPSWIN-00631 | Monday | MS4-SWT-055 | October | 2019-10-07 01:00 | 2019-10-07 03:00 | TBD | 2019-11-04 01:00 | 2019-11-04 03:00 | TBD | TBD
SWT-030 | Spring Valley | DPW2015-WPSWIN-00637 | Monday | MS4-SWT-030 | October | 2019-10-07 02:00 | 2019-10-07 04:00 | TBD | 2019-11-04 02:00 | 2019-11-04 04:00 | TBD | TBD
SWT-019 | Spring Valley | DPW2015-WPSWIN-00622 | Monday | MS4-SWT-019 | October | 2019-10-07 06:00 | 2019-10-07 08:00 | TBD | 2019-11-04 06:00 | 2019-11-04 08:00 | TBD | TBD
SDR-127 | Lakeside | DPW2015-WPSWIN-00733 | Tuesday | MS4-SDR-127 | October | 2019-10-08 01:00 | 2019-10-08 03:00 | TBD | 2019-11-05 01:00 | 2019-11-05 03:00 | TBD | TBD
SDR-098 | Lakeside | DPW2015-WPSWIN-00731 | Tuesday | MS4-SDR-098 | October | 2019-10-08 03:00 | 2019-10-08 05:00 | TBD | 2019-11-05 03:00 | 2019-11-05 05:00 | TBD | TBD
SLR-045 | Escondido | DPW2017-WPSWIN-01357 | Tuesday | MS4-SLR-045 | October | 2019-10-08 02:00 | 2019-10-08 04:00 | TBD | 2019-11-05 02:00 | 2019-11-05 04:00 | TBD | TBD
SLR-154 | Escondido | DPW2015-WPSWIN-00757 | Tuesday | MS4-SLR-154 | October | 2019-10-08 05:00 | 2019-10-08 07:00 | TBD | 2019-11-05 05:00 | 2019-11-05 07:00 | TBD | TBD
SLR-159 | Escondido | DPW2019-WPSWIN-02805 | Tuesday | MS4-SLR-159 | October | 2019-10-08 05:00 | 2019-10-08 07:00 | TBD | 2019-11-05 05:00 | 2019-11-05 07:00 | TBD | TBD
SDG-074 | 4S Ranch | DPW2015-WPSWIN-00604 | Wednesday | MS4-SDG-074 | October | 2019-10-09 02:00 | 2019-10-09 04:00 | TBD | 2019-11-06 02:00 | 2019-11-06 04:00 | TBD | TBD
SDG-077 | 4S Ranch | DPW2015-WPSWIN-00606 | Wednesday | MS4-SDG-077 | October | 2019-10-09 04:00 | 2019-10-09 06:00 | TBD | 2019-11-06 04:00 | 2019-11-06 06:00 | TBD | TBD
SDG-084 | 4S Ranch | DPW2015-WPSWIN-00607 | Thursday | MS4-SDG-084 | October | 2019-10-10 02:00 | 2019-10-10 04:00 | TBD | 2019-11-07 02:00 | 2019-11-07 04:00 | TBD | TBD
SDG-085 | 4S Ranch | DPW2015-WPSWIN-00608 | Thursday | MS4-SDG-085 | October | 2019-10-10 05:00 | 2019-10-10 07:00 | TBD | 2019-11-07 05:00 | 2019-11-07 07:00 | TBD | TBD
CAR-072 | San Marcos | DPW2015-WPSWIN-00724 | Friday | MS4-CAR-072 | November | 2019-11-01 03:00 | 2019-11-01 05:00 | TBD | 2019-11-29 03:00 | 2019-11-29 05:00 | TBD | TBD
SDG-275 | San Diego | DPW2019-WPSWIN-02919 | Saturday | MS4-SDG-275 | November | 2019-11-02 | 2019-11-02 02:00 | TBD | 2019-11-30 | 2019-11-30 02:00 | TBD | TBD
CAR-070 | San Marcos | DPW2015-WPSWIN-00721 | Sunday | MS4-CAR-070 | November | 2019-11-03 07:00 | 2019-11-03 09:00 | TBD | 2019-12-01 07:00 | 2019-12-01 09:00 | TBD | TBD
SDR-127 | Lakeside | DPW2015-WPSWIN-00733 | Sunday | MS4-SDR-127 | November | 2019-11-03 17:00 | 2019-11-03 19:00 | TBD | 2019-12-01 17:00 | 2019-12-01 19:00 | TBD | TBD
SWT-030 | Spring Valley | DPW2015-WPSWIN-00637 | Monday | MS4-SWT-030 | November | 2019-11-04 02:00 | 2019-11-04 04:00 | TBD | 2019-12-02 02:00 | 2019-12-02 04:00 | TBD | TBD
SLR-045 | Escondido | DPW2017-WPSWIN-01357 | Tuesday | MS4-SLR-045 | November | 2019-11-05 02:00 | 2019-11-05 04:00 | TBD | 2019-12-03 02:00 | 2019-12-03 04:00 | TBD | TBD
SDR-098 | Lakeside | DPW2015-WPSWIN-00731 | Wednesday | MS4-SDR-098 | November | 2019-11-06 03:00 | 2019-11-06 05:00 | TBD | 2019-12-04 03:00 | 2019-12-04 05:00 | TBD | TBD
SDR-207 | Lakeside | DPW2015-WPSWIN-00738 | Wednesday | MS4-SDR-207 | November | 2019-11-06 04:00 | 2019-11-06 06:00 | TBD | 2019-12-04 04:00 | 2019-12-04 06:00 | TBD | TBD
SDG-084 | 4S Ranch | DPW2015-WPSWIN-00607 | Wednesday | MS4-SDG-084 | November | 2019-11-06 20:00 | 2019-11-06 22:00 | TBD | 2019-12-04 20:00 | 2019-12-04 22:00 | TBD | TBD
SDG-072 | 4S Ranch | DPW2015-WPSWIN-00603 | Wednesday | MS4-SDG-072 | November | 2019-11-06 21:00 | 2019-11-06 23:00 | TBD | 2019-12-04 21:00 | 2019-12-04 23:00 | TBD | TBD
SDG-085 | San Diego | DPW2015-WPSWIN-00608 | Thursday | MS4-SDG-085 | November | 2019-11-07 05:00 | 2019-11-07 07:00 | TBD | 2019-12-05 05:00 | 2019-12-05 07:00 | TBD | TBD
SLR-154 | Escondido | DPW2015-WPSWIN-00757 | Thursday | MS4-SLR-154 | December | 2019-12-12 05:00 | 2019-12-12 07:00 | TBD | 2020-01-09 05:00 | 2020-01-09 07:00 | TBD | TBD
HST01 | Rainbow | DPW2019-WPSWIN-02972 | Thursday | MS4-HST01 | December | 2019-12-12 07:00 | 2019-12-12 09:00 | TBD | 2020-01-09 07:00 | 2020-01-09 09:00 | TBD | TBD
SDG-074 | San Diego | DPW2015-WPSWIN-00604 | Thursday | MS4-SDG-074 | December | 2019-12-12 03:30 | 2019-12-12 05:30 | TBD | 2020-01-09 03:30 | 2020-01-09 05:30 | TBD | TBD
SDG-077 | San Diego | DPW2015-WPSWIN-00606 | Thursday | MS4-SDG-077 | December | 2019-12-12 05:00 | 2019-12-12 07:00 | TBD | 2020-01-09 05:00 | 2020-01-09 07:00 | TBD | TBD
CAR-072 | San Marcos | DPW2015-WPSWIN-00724 | Friday | MS4-CAR-072 | December | 2019-12-13 02:00 | 2019-12-13 04:00 | TBD | 2020-01-10 02:00 | 2020-01-10 04:00 | TBD | TBD
CAR-070 | San Marcos | DPW2015-WPSWIN-00721 | Friday | MS4-CAR-070 | December | 2019-12-13 04:30 | 2019-12-13 06:30 | TBD | 2020-01-10 04:30 | 2020-01-10 06:30 | TBD | TBD
CAR-069 | San Marcos | DPW2015-WPSWIN-00718 | Friday | MS4-CAR-069 | December | 2019-12-13 02:00 | 2019-12-13 04:00 | TBD | 2020-01-10 02:00 | 2020-01-10 04:00 | TBD | TBD
SWT-019 | Spring Valley | DPW2015-WPSWIN-00622 | Sunday | MS4-SWT-019 | December | 2019-12-15 02:00 | 2019-12-15 04:00 | TBD | 2020-01-12 02:00 | 2020-01-12 04:00 | TBD | TBD
SWT-235 | Spring Valley | DPW2015-WPSWIN-00672 | Sunday | MS4-SWT-235 | December | 2019-12-15 03:00 | 2019-12-15 05:00 | TBD | 2020-01-12 03:00 | 2020-01-12 05:00 | TBD | TBD
SDR-127 | Lakeside | DPW2015-WPSWIN-00733 | Sunday | MS4-SDR-127 | December | 2019-12-15 16:00 | 2019-12-15 18:00 | TBD | 2020-01-12 16:00 | 2020-01-12 18:00 | TBD | TBD
SDR-203A | Lakeside | DPW2015-WPSWIN-00736 | Sunday | MS4-SDR-203A | December | 2019-12-15 15:30 | 2019-12-15 17:30 | TBD | 2020-01-12 15:30 | 2020-01-12 17:30 | TBD | TBD
SDG-072 | San Diego | DPW2015-WPSWIN-00603 | Monday | MS4-SDG-072 | December | 2019-12-16 21:30 | 2019-12-16 23:30 | TBD | 2020-01-13 21:30 | 2020-01-13 23:30 | TBD | TBD
SDR-098 | Lakeside | DPW2015-WPSWIN-00731 | Tuesday | MS4-SDR-098 | December | 2019-12-17 02:00 | 2019-12-17 04:00 | TBD | 2020-01-14 02:00 | 2020-01-14 04:00 | TBD | TBD
SDR-097 | Lakeside | DPW2015-WPSWIN-00727 | Tuesday | MS4-SDR-097 | December | 2019-12-17 03:00 | 2019-12-17 05:00 | TBD | 2020-01-14 03:00 | 2020-01-14 05:00 | TBD | TBD
SDR-204A | Lakeside | DPW2015-WPSWIN-00737 | Wednesday | MS4-SDR-204A | December | 2019-12-18 05:00 | 2019-12-18 07:00 | TBD | 2020-01-15 05:00 | 2020-01-15 07:00 | TBD | TBD
CAR-059 | San Marcos | DPW2015-WPSWIN-00744 | Wednesday | MS4-CAR-059 | December | 2019-12-18 07:30 | 2019-12-18 09:30 | TBD | 2020-01-15 07:30 | 2020-01-15 09:30 | TBD | TBD
SLR-095 | Escondido | DPW2015-WPSWIN-00761 | Wednesday | MS4-SLR-095 | December | 2019-12-18 13:00 | 2019-12-18 15:00 | TBD | 2020-01-15 13:00 | 2020-01-15 15:00 | TBD | TBD
SDG-080 | San Diego | DPW2015-WPSWIN-00660 | Wednesday-Thursday | MS4-SDG-080 | December | 2019-12-18 22:00 | 2019-12-20 | TBD | 2020-01-15 22:00 | 2020-01-17 | TBD | TBD
#REF!
198